## Fall 2018
DEBRIEF NOTES ¦ Event Name
[event date]
Count of Notes | 13
Category | Notes From | Debrief Notes | Actions Taken
Invitations | Kira | Order more Convocation invitations for Spring Convocation (only 9 left).
Speaking Program | Kira | Always request Elder to do the traditional welcome at the Chancellors dinner for spring and fall convocations.
MECS/Catering | Lisa | The Thursday lunch buffet at the DAC was excellent but a little too spicy for the average person. Suggestion to keep spices mild. | Feedback shared with MECS and the caterer.
Marshals | Lisa/Gloria | John and Wanda did an excellent job as faculty marshals. Consider asking them to help again.
Head Usher | Lisa | Create Head Usher task checklist for onsite tasks. | A checklist has been created and distributed to the Head Ushers.
Book of Words | Tia | Add a 'last updated' date on the first page of the book of words to make it easier to track the most up to date copy.
Reserved Seating | Tia | All guests requesting additional seats should continue to do so by emailing the data coordinator 3 weeks prior to the event. This worked well this time around.
Invitations | Tia | Order more C&E #4 envelopes from Doc Sol. | Envelopes have been ordered.
Signage | Lisa | Update signage plan in Convo mall e.g. adjust placement of enter/exit signs at the back of the mall and placement of 'quiet please, ceremony in process'.
Crowd Control | Fiona | Crowd control was difficult for student ushers to manage on the balcony near the media area. Consider adding a 10 ft span of pipe and drape at the top of the stairs. Add signage that says 'media access only'.
Accessibility | Rosa | The wheelchair sign out process worked well at the AQ coat check. | Continue offering wheelchair sign out in the AQ during Convocation.
Parking | David | Parking ran smoothly. Gravel lot worked well. There were low traffic volumes.
Regalia Room | Kris | Closing the regalia room at a fixed time (5:15 pm) worked well.